## Slide 1
Part 1
Welcome and Introduction- Sandy Guryan
Highlights of 8 MSBA Modules- Alex Valcarce
Project Timeline- Josh Morse
Role & Integration of SBC- Alex Valcarce
Part 2
Committee Organization
Committee Authorizations
Next Steps 3-6 Months
CABOT ELEMENTARY SCHOOL PROJECT
CABOT SCHOOL
BUILDING
COMMITTEE
Agenda
April 17, 2014

## Slide 2: MSBA Process Modules Overview
Eligibility
Duration
3 Months
Team Selection
6 Months
Feasibility
Study
Schematic Design
Project
Funding
Documents
Construction
Close Out
12-18 months
4 months
2 months
12-15 months
18-20 months
2 months
CABOT ELEMENTARY
SCHOOL PROJECT
CABOT SCHOOL
BUILDING
COMMITTEE

## Slide 3: MSBA Process
ELIGIBILITY
TEAM SELECTION
FEASIBILTY STUDY
ACCEPTANCE INTO ELIGIBILITY MODULE
Certify Program Compliance & Enrollment Projection
Form School Building Committee (SBC)
Provide Maintenance / Capital Improvements Information
Approve Feasibility Study Funding
Sign Feasibility Study Agreement
SELEC T OWNER’S PROJEC T MANAGER (OPM)
City / SBC advertises, Interviews, Ranks & Selects OPM
City Negotiates OPM Services Contract
MSBA OPM Panel Approves Selected OPM
SELECT DESIGNER
City advertises Request for Services (RFS) for Designer
City assigns three (3) members to MSBA Designer Selection Panel
Designer Selection Panel Ranks Designers
City Negotiates Design Services Contract.
CONDUCT FEASIBILITIY STUDY
Designer & OPM Develop Feasibility Study Alternative Concepts
City approves Preferred Alternative
MSBA approves Feasibility Study & Preferred Alternative
CABOT ELEMENTARY
SCHOOL PROJECT
CABOT SCHOOL
BUILDING
COMMITTEE

## Slide 4: MSBA Process (cont)
PROJECT
FUNDING
CONSTRUCTION
PROJECT CLOSE-OUT
DESIGN & CONSTRUCTION DOCUMENTS
MSBA performs final audit, determines final total grant amount
City with OPM and MSBA monitor construction progress
City’s Design Team advances design and construction documents
MSBA monitors project progress
APPROVE PROJECT FUNDING
MSBA determines Financial Assistance
City & MSBA establish Scope & Budget Agreement
City approves Project Funding
SCHEMATIC DESIGN
DEVELOP SCHEMATIC DESIGN
Develop Final Design Program and Robust Schematic
Establish Scope, Budget and Final Schedule
MSBA approves schematic design
City site plan approvals
CABOT ELEMENTARY
SCHOOL PROJECT
CABOT SCHOOL
BUILDING
COMMITTEE

## Slide 5: Typical MSBA Funded Project Timeline
CABOT SCHOOL BUILDING COMMITTEE
CABOT ELEMENTARY SCHOOL PROJECT

## Slide 6
Design Review Committee
School Building Committee
Cabot
CABOT ELEMENTARY
SCHOOL PROJECT
CABOT SCHOOL BUILDING COMMITTEE
School Building Committee
Role & Process

## Slide 7: Selection of Owner’s Project Manager
Designer Selection Cmte
Board of Aldermen
School
Committee
MSBA
School Building Cmte
Cabot Working Group
CABOT ELEMENTARY
SCHOOL PROJECT
CABOT SCHOOL BUILDING COMMITTEE
Executive Office Negotiates

## Slide 8: Selection of Designer
Designer Selection Cmte
Board of Aldermen
School
Committee
School Building Cmte
Designer Selection Panel
Executive Office Negotiates
Cabot Working Group
CABOT ELEMENTARY
SCHOOL PROJECT
CABOT SCHOOL BUILDING COMMITTEE

## Slide 9
Design Review Committee
Board of
Aldermen
School Committee
Feasibility & Design Approval
School Building Cmte
MSBA
CABOT ELEMENTARY
SCHOOL PROJECT
CABOT SCHOOL BUILDING COMMITTEE
Cabot Working Group
School Building Cmte

## Slide 10: Agenda April 17, 2014
CABOT SCHOOL BUILDING COMMITTEE
PART 2
Committee Organization:
Determine Requirements for a Quorum
Determine Number of Votes Required for Recommendations to MSBA
Committee Authorizations:
Authorize Designer Selection Committee (DSC)
To Select Owner’s Project Manager (OPM)
Authorize Request for Services (RFS)
Authorize Advertisement of OPM RFS
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 11: CSBC Committee Organization
CABOT SCHOOL BUILDING COMMITTEE
Members Required for A Quorum:
Motion:
Moved that a majority of the voting members of the Cabot School Building
Committee constitute a quorum.
Vote required for Approval of Matters:
Motion:
Moved that matters coming before the Cabot School Building Committee
that require a vote be approved by a majority of those voting members present.
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 12: Designer Selection Committee
CABOT SCHOOL BUILDING COMMITTEE
Designer Selection Committee
Required under Section 5-35 of Revised City Ordinances
Committee Members:
Joseph Michelson
Mr. Michelson has over fifty years’ experience in the construction industry. He has been involved with numerous projects both in the public and private sector. He has also served as chairman of the Newton Designer Selection Committee since 1972.
Arthur Cohen, FAIA, LEED AP
As a founding principal at ARC with more than forty years of experience, Arthur has led the design of many of award-winning projects. Arthur has created nationally-recognized buildings for public and private clients. He is a LEED AP and actively promotes sustainable design principles. Currently Arthur serves as Chair for the Newton Design Review Committee as well.
Howard Goldberg, P.E.
Mr. Goldberg has over 40 years of experience in the management, design and construction of a wide variety of public and private projects in diverse fields. Howard has been involved in value engineering workshops, technical advisory groups and performed constructability reviews.
Lawrence C Bauer, AIA
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 13: Designer Selection Committee
CABOT SCHOOL BUILDING COMMITTEE
Committee Members:
Lawrence C Bauer, AIA
A thirty-four year principal of Solomon+Bauer Architects Inc, Larry has played a lead role in projects for museums, colleges and universities. Several projects have combined Larry’s design skills with his expertise in historic preservation. He is a former member of the Newton Historical Commission, and served as its chair and its secretary.
Richard F. Griffin, AlA
Mr. Griffin is a founding partner of the architectural firm Scott/Griffin Architects, Ltd. where he serves as the president of the corporation. Mr. Griffin provides expertise in the area of strategic planning of issues involving zoning, land-use, special permitting and public processes.
Peter Vanderwarker
Peter is an experienced writer and photographer of architectural projects and architectural history. His works include numerous publications on the City of Boston and significant architectural buildings and landmarks. His experience includes documentary film production and he has been an instructor in Architectural Design at the Boston Architectural Center.
CABOT
ELEMENTORY
SCHOOL PROJECT

## Slide 14: Designer Selection Committee
Benjamin Tucker, LEE AP
Mr. Tucker is a senior construction professional with extensive knowledge of real estate development, design and construction processes. He is a LEED Accredited Professional with experience in LEED rating systems and sustainable development strategies. With nearly twenty years of industry experience including fifteen years managing commercial real estate developments and construction projects as well as three years of residential architecture, design and construction; Ben is a strong contributor, adept leader, and key resource for all aspects of development, design and construction.
James Powers, P.E.
Mr. Powers is a civil engineering professional with broad experience in many aspects of engineering and construction projects both nationally and internationally. His career includes positions with Metcalf & Eddy (now AECOM), and with the Massachusetts Water Resources Authority (M\VRA). Focus at Metcalf & Eddy was on planning and designing facilities while the focus at the MWRA was on implementing portions of a major capital improvement program. In addition to his technical expertise areas of specialization include staff recruitment, submittal reviews and approvals, and procurement of professional engineering services.
CABOT
ELEMENTORY
SCHOOL PROJECT
CABOT SCHOOL BUILDING COMMITTEE

## Slide 15: Owner’s Project Manager Procurement
CABOT SCHOOL BUILDING COMMITTEE
Delegation Regarding Procurement of OPM Services:
Motion:
Moved that the Designer Selection Committee established by Section 5-35 of the Revised Ordinances of the City of Newton be authorized to oversee the selection of the OPM in accordance with the requirements of City ordinances, state laws and regulations, and Massachusetts State Building Authority’s requirements for the Cabot Elementary School Project.
Composition of Selection Committee for Procurement of OPM Services:
Motion:
Moved that the composition of the Designer Selection Committee for procurement of OPM services for the Cabot Elementary School Project shall be in accordance with the requirements of Section 5-36 of the Revised Ordinances of the City of Newton.
CABOT
ELEMENTORY
SCHOOL PROJECT

## Slide 16: Owner’s Project Manager Request For Services
CABOT SCHOOL BUILDING COMMITTEE
Project Objectives and Services:
Reviewing and assessing the documentation of existing conditions at the Cabot Elementary School, the educational program, the alternative conceptual designs and their constructability, and developing cost estimates for each of the design solutions.
Massachusetts Historical Commission - the Cabot Elementary School will be brought to the Newton Historic Commission on April 24, 2014 for a property review and determination.
Detailed Comprehensive Project Schedule - to achieve specified start and completion milestones. The Project Schedule construction start in the summer of 2017 and completion for September 2019.
Incorporating the City of Newton’s approval processes into the project schedule and deadlines of the MSBA approval process.
Ensuring that the educational program is fully understood and incorporated into the process.
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 17: Owner’s Project Manager Request For Services
CABOT SCHOOL BUILDING COMMITTEE
Project Objectives and Services:
Developing a design that is of high quality, efficient, cost effective, and that conforms to the educational program and the Massachusetts High Performance Green Schools Guidelines (MA-CHPS Guidelines); and LEED for Schools at a minimum and complying with all applicable regulatory requirements including the Massachusetts Stretch Code which has been adopted by the City of Newton.
Development and evaluation of creative energy efficiency solutions and innovative alternative sustainable design solutions, including but not limited to active/passive solar, geothermal, etc., and identifying alternate funding sources, first costs and paybacks.
Collaborating in the development of Iterative Whole Building Energy Models. The project will require additional modeling beyond that which may be required in fulfillment of other project objectives. Prior to the conclusion of the Feasibility Phase the project will seek to establish the lowest possible Energy Use Intensity (EUI) based on Life Cycle Costs and available funding.
Developing accurate and complete cost estimates, including life cycle cost analysis of operating the school as it relates to future operational budgets.
Determining appropriateness of CM-at-Risk delivery Method for the Project.
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 18: Owner’s Project Manager Request For Services
CABOT SCHOOL BUILDING COMMITTEE
Evaluation Criteria:
The Project Director shall be a person who is registered by the Commonwealth of Massachusetts as an architect or professional engineer and who has at least 5 years’ experience in the construction and supervision of construction and design of public buildings: or,
if not registered as an architect or professional engineer, the Project Director must be a person who has at least 7 years of experience in the construction and supervision of construction and design of public buildings.
Relevant Experience
Past performance of the Respondent, if any, with regard to public, private, DOE funded and MSBA-funded school projects across the Commonwealth
B. Knowledge of Codes, Procurement and Sustainability
Provide examples of and demonstrate the Respondents past performance and thorough knowledge of the Massachusetts State Building Code.
Provide examples of and demonstrate the Respondents past performance and thorough knowledge of Commonwealth construction procurement laws.
Thorough knowledge and experience with CM-at-Risk Procurement methodology.
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 19: Owner’s Project Manager Request For Services
CABOT SCHOOL BUILDING COMMITTEE
Evaluation Criteria:
4. Familiarity with Massachusetts-CHPS (MA-CHPS) High Performance Green Schools Guidelines and USGBC LEED for Schools (LEED-S).
5. Thorough knowledge and demonstrated experience with life cycle cost analysis cost.
6. Knowledge of the purpose and practices of the services of Building Commissioning Consultants.
C Project Understanding and Approach
1. Management approach: .
D. Project Team / Commitments / Availability
Key personnel:
E. Firm Qualifications / Capacity
Capacity and skills: Identify existing employees by number and area of expertise (e.g. field supervision, cost estimating, schedule analysis, value engineering, constructability review, quality control and safety). Identify any services to be provided by Sub-consultants.
Provide references as set forth in Attachment C, and from Owner’s, Designers and Contractors who have all collaborated together with the Respondent on projects of similar size and complexity.
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 20: Owner’s Project Manager Request For Services
CABOT SCHOOL BUILDING COMMITTEE
Evaluation Criteria:
3. Identify the Respondent’s current and projected workload for projects estimated to cost in excess of $1.5 million.
4. Financial Stability: Provide two years of financial statements including current balance sheet, income statement, and a Certificate of Insurance that certifies the OPM can meet the insurance requirements set forth in the Contract for Project Management Services, Attachment B.
5. Quality of work and level of performance. The Owner will seek evidence of practicality, creativity, attention to detail and follow through, as well as professional competence.
6. Ability to schedule, undertake and complete responsibilities in a timely manner.
CABOT
ELEMENTORY
SCHOOL PROJECT

## Slide 21: OPM RFS Advertisement
CABOT SCHOOL BUILDING COMMITTEE
Owner's Project Management Services
for the
Cabot Elementary School Project
by the City of Newton
Cabot School Building Committee
City of Newton
1000 Commonwealth Avenue
Newton, MA 02459
(617) -796-1220
The City of Newton, ("Owner"), acting through the Cabot School Building Committee and Designer Selection Committee, is seeking the services of a qualified "Owner's Project Manager" as defined in Massachusetts General Laws Chapter 149, Section 44A1/2 and as further defined by the provisions of this Request for Services ("RFS"), to provide Project Management Services for Feasibility and Schematic Design for addition to and /or renovation of; or replacement of the Cabot Elementary School ("School") in Newton, Massachusetts ("Project"). The Owner may elect to extend the contract to include Design Development, Construction Documents, Bidding and Award, Construction, and Project Close-out services.
Proposals are to be delivered in person or by certified/express mail to the Purchasing Department located in Newton City Hall, 1000 Commonwealth Avenue, Newton, MA 02459. All proposals must be received by 10:00 AM (EDT) on May 14, 2014, to be considered. Proposals submitted by fax or by electronic mail will not be considered.
An informational briefing session and facility tour for project managers will be held on May 6, 2014 at 3:30 p.m. (EDT) at the library of the Cabot Elementary School, 229 Cabot St., Newton, MA.
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 22: OPM RFS / Advertisement Authorization
CABOT SCHOOL BUILDING COMMITTEE
Authorize Request and Advertise for OPM Services:
Motion:
Moved that the City of Newton acting through its Public Buildings Commissioner and Designer Selection Committee issue a Request for Services for an OPM for the Cabot Elementary School Project and place an advertisement for such RFS at the earlier date possible.
CABOT
ELEMENTARY
SCHOOL PROJECT

## Slide 23: CSBC April 17, 2014
CABOT SCHOOL BUILDING COMMITTEE
Schedule:
OPM Selection May – June 2014
Designer Selection June – August 2014
Feasibility Study Kick-Off September- 2014
Information:
Available at
http://www.newtonma.gov/gov/building/Cabot_school/committees/default.asp
Questions:
Meeting Concluded:
Thank You for your Participation
CABOT
ELEMENTARY
SCHOOL PROJECT