## DPW Schedule
DPW WEEKLY CONSTRUCTION SCHEDULE
| WEEK OF | 2024-11-18
TENTATIVE
|  |  | STATUS & | COMPLETION
ACTIVITY |  | LOCATION | DATES | DATE | IMPACT | CONTRACTOR | LEAD DIVISION | CONTACT | PHONE
TRAFFIC SIGNAL INSTALLATION |  | Mass Pike Eastbound off ramp at Centre Ave | Nov 18 - 22 | November | night work, lane closures | Mass DOT | Transportation | N. Codd | 617-796-1020
Newton Corner
WATER METER REPLACEMENTS |  | All properties | Nov 18 - 22 | 2024 | temp water shut off during installation | Bayside Engineering | Utilities | D. Valovcin | 617-796-1640
ROADWAY REHABILITATION |  | Commonwealth Ave and Carriage Way Auburndale |  |  |  | W.L. French | Engineering | J. Daghlian | 617-796-1020
SIDEWALKS, CURB, MILLING, PAVING |  | (Hotel entrance east of Auburn St, to Higgins St) |  |  |  | Mass DOT | Transportation | I. Prizant | 617-796-1020
|  | Phase 1, south side of roadway | Nov 18 - 22 | 2024 |  |  | Howard Stein Hudson | Chris Malsch
|  | Phase 2, north side of roadway | starts 2025 | 2025
|  | Phase 3, median islands | starts 2025 | 2025
ROADWAY REHABILITATION |  | Hammond Pond Parkway (Boylston to Beacon) | Nov 18 - 22 | fall | lane closures, detours | C. Naughton | DCR | J. Daghlian | 617-796-1020
INTERSECTION IMPROVEMENTS |  | Hammond Pond Parkway at Beacon St Intersection | Nov 18 - 22 |  |  |  |  | I. Prizant | 617-796-1483
ROADWAY REHABILITATION |  | Needham St (Charles River Bridge to Winchester St) | Nov 18 - 22 | May 15, 2025 |  | P. Gioioso | Mass DOT | E. Feeley | C. Sabella
ROADWAY REHABILITATION |  | Winchester St (Needham St to Boylston St) | Nov 18 - 22 | May 15, 2025 |  |  | Engineering | J. Daghlian | 617-796-1020
ROADWAY REHABILITATION |  | Auburndale Ave, Oak Ave | Nov 18 - 22 | November | line striping | D&R | Engineering | J. Pisano | 617-796-1020
SIDEWALKS, CURB, MILLING, PAVING |  | Valentine St | Nov 18 - 22 | November | paving Nov 15 - 18 |  | EPG
SEWER MAIN CLEANING AND LINING |  | Project 8, Various Locations | Nov 18 - 22 |  |  | National Water Main | Utilities | M. Ovaska | 617-796-1640
|  | post construction inspections |  |  |  |  | Weston & Sampson
|  | Parker St to Winchester St | upcoming
SEWER MAIN CLEANING AND LINING |  | Project 9, Various Locations | Nov 18 - 22 | winter |  | Insituform | Utilities | M. Ovaska | 617-796-1640
SEWER SPOT REPAIRS |  | Alban Rd | Nov 20 |  |  | Paolini | Weston & Sampson
INTERSECTION IMPROVEMENTS |  | Oak St at Chestnut St, Pettee Square | Nov 18 - 22 | substantial completion 12/24 |  | A.R. Belli | Transportation | I. Prizant | 617-796-1020
[7 empty] | TEC | Patrick Hanlon
WATER MAIN REPLACEMENT |  | Bothfield Rd | Nov 18 - 22 | November | lane closures | Cedrone | Engineering | A. Stellato | 617-796-1020
|  | Wells Ave | upcoming |  | lane closures
WATER MAIN INSTALLATION |  | Commonwealth Ave at MBTA Station near BC | upcoming November |  | lane closure | N. Granese | Utilities | D. Valovcin | 617-796-1640
COLD IN PLACE ASPHALT RECYCLING |  | Austin St (Lowell Ave to Chestnut St) | Nov 18 - 22 | November | paving Nov 19 - 20 | Indus, D&R | Engineering | J. Pisano | 617-796-1020
SIDEWALKS, PAVING |  | Albemarle Rd (southbound Crafts St to Watertown St) | Nov 18 - 22 | November | paving Nov 19 - 20 |  | EPG
CRACK SEALING |  | City Hall Campus | upcoming |  |  | Indus | Engineering | J. Pisano | 617-796-1020
EPG
ADA RAMP INSTALLATION |  | Beacon St (Locke Rd to Metacomet Rd) | Nov 18 - 22 |  |  | Charles Construction | Engineering | J. Pisano | 617-796-1020
INTERSECTION IMPROVEMENTS |  | Chestnut St at Fuller St | Nov 18 - 22 | November | line striping | Charles Construction | Engineering | J. Pisano | 617-796-1020
DRAINAGE IMPROVEMENTS |  | Rumford Ave facility | Nov 18 - 22 |  |  | Streets | Streets | M. McKay | 617-796-1020
Ramp lane closures for Mass Pike and I-95 north:
Exit 123A from I-90 eastbound to I-95 northbound will be reduced to one lane, and is expected to continue until fall of 2027.
Exit 39B from I-95 northbound to I-90 will be reduced to one lane, and is expected to continue until fall of 2027.
GAS MAINS | [5 empty] | National Grid, Feeney | Engineering | K. Ritcey | 617-796-1020
| gas main replacement, services | Commonwealth Ave (Melrose to I-95) | Nov 18 - 22 | November | lane closures, detours
| gas main replacement, services | Centre St (Alderwood Rd to Commonwealth Ave) | Nov 18 - 22 | November | lane closures, detours
| gas main replacement, services | Centre St Bridge (west), Richardson to Washington St | Nov 18 - 22 | November | day-night work, lane closure
| gas main replacement, services | Elliot St #144 - #251 (Boylston to Circuit), including: | Nov 18 - 22 | March
| gas main replacement, services | Chandler Pl, Cheney St, Elliot Ter, Linden St, Mechanic and Wetherell St |  | March
| gas main replacement, services | Jasset St (1 to 49) | Nov 18 - 22 | November
| gas main replacement, services | Boylston St # 504-528 | Nov 18 - 22 | November | night work
| gas main replacement, services | Hansen Rd (Hay Rd, R Rdwy, S Rdwy, T Rdwy, Colella Rd) | Nov 18 - 22 | 2025
| gas main replacement, services | Elliot St (Linden to Chestnut) | upcoming
| gas main replacement, services | Lexington St (Auburn St to Auburndale Ave) | upcoming |  | lane closures, detours
| gas main replacement, services | Highland Ave (11 - 66) | upcoming
| gas main replacement, services | Centre St (Commonwealth Ave to Cypress St) | upcoming |  | lane closures, detours
| gas main replacement, services | Walnut St (Lake St to Centre St) | upcoming |  | day-night work, detours
| gas main replacement, services | Linwood Ave (Adams St to Broadway) | upcoming
| gas main replacement, services | Chestnut Hill Rd, including: | upcoming
| gas main replacement, services | Essex, Gate House Rd, Nancy, Meigh, Gate House Terr | upcoming
ELECTRICAL CONDUIT
|  | Tower Rd (to Northland Site) | Nov 18 - 22 |  |  | Eversource, Riley Bros | Engineering | K. Ritcey | 617-796-1020
|  | Christina St (Needham St to Rowland St) | Nov 18 - 22 |  |  | Eversource, Mirra | Engineering | K. Ritcey | 617-796-1020
|  | Auburn St (Lexington St west to Commonwealth Ave) | upcoming
Definition of Terms
Roads:
Cold Planing - the removal of existing asphalt surface (1-1/2 inch) by milling
Paving - Placing new 1-1/2 inch layer of asphalt (bituminous) overlay
Water Mains:
Cleaning and Lining - Clean the interior of the water pipe and line with cement, replace water services from main to property line
Replacement - Replace the water pipe with new pipe, and replace water services from main to property line
Sewer Mains:
Heavy Cleaning - Clean interior of sewer pipe and manholes, and remove all sediment to maintain flow
Rehabilitation - Clean interior of sewer pipe and manholes, and remove all sediment, line sewer pipe with inverted plastic liner, seal all manholes with cement liner
Public Notification - Flyers, robo-calls, sign boards, sandwich boards, letters
Impact - Road closure, detours, no parking, noise ordinance waiver
WORK TENTATIVELY SCHEDULED:
ROAD DIET PILOT PROGRAM |  | Washington St (Chestnut St to Lowell Ave) | upcoming 2025 |  | lane closures | I. W. Harding | Planning | J.Martin | 617-796-1030
| CONSTRUCTION | [5 empty] | Howard Stein Hudson | C. Malsch
ROADWAY REHABILITATION |  | Homer St (Commonwealth to Walnut) | upcoming 2025
SIDEWALKS, CURB, MILLING, PAVING |  | Walnut St (Commonwealth to Homer) | upcoming 2025
MAINTENANCE OVERLAY |  | Woodchester Dr | upcoming 2025
SIDEWALKS INSTALLATION |  | Ward School area | upcoming 2025 |  |  | Commonwealth Constr | Engineering | J. Pisano | 617-796-1020
SIDEWALKS INSTALLATION |  | Underwood School area | spring 2025 |  |  |  | Engineering | J. Pisano | 617-796-1020
SIDEWALKS, CURB |  | Border St | spring 2025 |  | punch list | Holcim | Engineering | J. Pisano | 617-796-1020
|  | Wheeler Rd | spring 2025 |  | punch list |  | EPG
ADA RAMP INSTALLATION |  | Beacon St at Sumner St and Langley Rd | upcoming 2025 |  |  | Charles Construction | Engineering | J. Pisano | 617-796-1020
INTERSECTION IMPROVEMENTS |  | Commonwealth Ave at Temple St | upcoming 2025 |  |  |  | Engineering | J. Pisano | 617-796-1020
MWRA WATER MAIN INSTALLATION |  | Ward St (Waverley Ave to Centre St) | spring 2025 | 2026 | lane closures | P. Gioioso | MWRA | Ali Kowsari
|  | Centre St (Ward St to Grafton St) | spring 2025 |  | lane closures |  | Engineering | A. Stellato | 617-796-1020
|  | Grafton St (Centre St to Commonwealth Ave) | spring 2025 |  | lane closures
INTERSECTION IMPROVEMENTS |  | California St at Bridge St | spring 2025 |  |  | Riverdale Development | Engineering | M. Mastroianni | 617-796-1020
ADA RAMPS | [7 empty] | J. Daghlian
ROADWAY PAVING |  | Boylston St, Rt 9, Chestnut St to Hammond St | spring 2025 |  |  | Mass DOT
TEST BORINGS |  | Commonwealth Ave at Centre St southeast corner | upcoming |  |  |  | Transportation | I. Prizant | 617-796-1020
TEST BORINGS |  | Newton Corner | upcoming |  |  |  | Transportation | I. Prizant | 617-796-1020
GAS MAINS |  | The work below may be scheduled, pending National Grid work priorities : |  |  |  | National Grid, Feeney | Engineering | K. Ritcey
Washington St (Chestnut St to Lowell Ave)
Collins Rd, Southwick, Devonshire gas main and (16)services
Grove St (I-95 to MBTA Bridge)
Grove St 547-687
Grove St at Colgate and Hagar
Boylston St #616-692
Walnut Hill Rd
Oakdale Rd
Moody St #15-56
Hammond Pond Pkwy at Boylston St